## SkillWise_Solo_Backlog
Sprint | Feature | User Story | Task | Tech Stack | Definition of Done | Difficulty
Story 1.1 | User Authentication | As a user, I want to create an account so that I can save my learning progress. | Signup form UI (React + RHF + Zod) | React, React Hook Form, Zod, Axios | Form renders, validates inputs, sends POST to /signup, error states handled. | 2
Story 1.2 | User Authentication | As a user, I want to log into my account so that I can access my dashboard. | Login form UI | React, React Hook Form, Axios | Login form works with JWT, error handling included, redirects to dashboard. | 2
Story 1.3 | User Authentication | As a developer, I want backend routes for signup, login, and logout so that users can authenticate. | Auth endpoints /signup, /login, /logout | Node.js, Express, JWT, bcrypt, Prisma | Endpoints implemented; users saved in DB; passwords hashed. | 3
Story 1.4 | User Authentication | As a user, I want to stay logged in securely so that I don’t have to re-login constantly. | JWT session handling | Express middleware, JWT refresh tokens, httpOnly cookies | Middleware validates JWT; refresh token endpoint works; session persists on reload. | 3
Story 1.5 | User Authentication | As a developer, I want a users table so that account data is stored persistently. | Users table migration | PostgreSQL, Prisma migration | Table created with id, email, password_hash, timestamps. | 2
Story 1.6 | Dashboard | As a user, I want a dashboard shell so that I can see my goals and challenges in one place. | Dashboard shell page | React Router, MUI/Tailwind | Dashboard route created, nav bar present, placeholder sections for goals/challenges. | 2
Story 1.7 | Testing | As a developer, I want automated tests for authentication so that I can confirm it works correctly. | Unit tests for auth endpoints | Jest, Supertest | Tests cover signup, login (valid + invalid), logout; pass in CI. | 2
Story 1.8 | DevOps | As a developer, I want a containerized environment so that I can run API and DB locally. | Docker Compose setup | Docker, Docker Compose, Postgres, Node.js | `docker-compose up` starts API + DB; app connects successfully. | 3
Story 2.1 | Goals | As a user, I want to create a learning goal so that I can track my progress. | Goal creation form | React, RHF, Axios | Form posts to backend; success shows in dashboard. | 2
Story 2.2 | Goals | As a developer, I want endpoints for goals so that users can manage their learning journey. | Goals CRUD endpoints | Express, Prisma, Postgres | CRUD endpoints implemented, linked to DB. | 3
Story 2.3 | Goals | As a developer, I want a goals table so that I can persist user-defined goals. | Goals table migration | Prisma migration | Table includes title, description, user_id, target_date. | 2
Story 2.4 | Challenges | As a user, I want to see my challenges displayed as cards so that I can easily browse them. | Challenge card UI | React, MUI/Tailwind | Cards render with title, description, and status. | 2
Story 2.5 | Challenges | As a developer, I want endpoints for challenges so that I can persist tasks linked to goals. | Challenges CRUD endpoints | Express, Prisma, Postgres | CRUD for /challenges works, linked to goals. | 3
Story 2.6 | Progress | As a user, I want a progress bar so that I can see my completion percentage. | Progress bar component | React, Recharts | Progress bar dynamically updates when challenges marked complete. | 2
Story 2.7 | Testing | As a developer, I want an end-to-end test so that I can confirm the workflow works. | Cypress smoke test | Cypress | Covers login → create goal → add challenge → mark complete. | 3
Story 2.8 | DevOps | As a developer, I want CI setup so that tests run automatically on every PR. | GitHub Actions CI | GitHub Actions, Jest, Cypress | Workflow runs lint + unit tests + Cypress test on PR. | 3
Story 3.1 | AI Challenges | As a user, I want to generate a challenge from AI so that I don’t have to design one myself. | Generate challenge button + modal | React, Axios | Button sends request to /ai/generateChallenge; result displays in modal. | 2
Story 3.2 | AI Challenges | As a developer, I want an AI endpoint so that I can provide tailored practice challenges. | AI challenge endpoint | Express, OpenAI API, Prisma | /ai/generateChallenge returns challenge; logs prompt/response. | 3
Story 3.3 | AI Challenges | As a developer, I want reusable AI prompts so that challenge generation is consistent. | AI prompt template | Node.js service file | Template created with placeholders; test harness verifies responses. | 2
Story 3.4 | AI Feedback | As a user, I want to submit work so that I can get AI feedback. | Submission form UI | React, file input/text area | Form submits content to backend /ai/submitForFeedback. | 2
Story 3.5 | AI Feedback | As a developer, I want an endpoint for feedback so that users can receive AI evaluations. | AI feedback endpoint | Express, OpenAI API, Prisma | Endpoint saves submission, stores AI response. | 3
Story 3.6 | AI Feedback | As a developer, I want to persist feedback so that users can review it later. | AI feedback table | Prisma migration | Table created with submission_id, prompt, response. | 2
Story 3.7 | Testing | As a developer, I want snapshot tests for AI responses so that they remain consistent. | Snapshot test AI responses | Jest | Tests run with sample prompts; snapshots pass. | 2
Story 3.8 | DevOps | As a developer, I want error tracking so that I can monitor app failures. | Sentry logging | Sentry SDK FE + BE | Sentry captures FE/BE errors; test error generates alert. | 3
Story 4.1 | Gamification | As a user, I want to see a leaderboard so that I stay motivated by competition. | Leaderboard UI | React, Recharts | Leaderboard displays users and points sorted descending. | 2
Story 4.2 | Gamification | As a developer, I want a backend endpoint so that the leaderboard updates with points. | Leaderboard endpoint | Express, Prisma | /leaderboard/update stores and fetches leaderboard scores. | 3
Story 4.3 | Peer Review | As a user, I want to submit a peer review so that I can help teammates learn. | Peer review UI | React, form component | UI posts to /peer/review; reviews displayed in dashboard. | 2
Story 4.4 | Peer Review | As a developer, I want to store peer reviews so that feedback is persistent. | Peer review endpoint | Express, Prisma | Endpoint saves review with reviewer_id, submission_id, comments, outcome. | 3
Story 4.5 | Testing | As a developer, I want accessibility tests so that the app works for all users. | Accessibility tests | axe-core, Cypress | Dashboard tested; top 3 violations fixed. | 2
Story 4.6 | DevOps | As a developer, I want production Docker images so that the app runs reliably in deployment. | Production Docker build | Dockerfile multi-stage build | Docker image builds; healthchecks pass. | 3
Story 4.7 | DevOps | As a developer, I want CI/CD deployment so that the app launches automatically. | GitHub Actions deploy | GitHub Actions, Vercel (FE), Render (BE) | Workflow deploys both services on merge to main. | 3
Story 4.8 | Docs | As a developer, I want clear documentation so that anyone can run and maintain the app. | Runbook + Swagger docs | Swagger, Markdown | Swagger docs live at /docs; Runbook explains env vars, deploy steps. | 2